## A2A Integrations-Interfaces
Consolidated list of Integrations
Sr. No. | Business Area | Process Group (L1) | Process Scenario (L2) | Business Scenario (L3) | Integration Requirements | From Application | To Application | TCS Owner | Integration Method | Existing Integration | Connectivity Type | SSL Certificate & Token Required? | Remarks | SI responsible
1 | Finance | Invoice to Pay | Invoice Receipt | Digital invoices, Handwritten invoices | Central mailbox - Outlook with VIM, NA | Outlook email services | SAP-VIM | Vaibhav | Real Time |  |  |  |  | #REF!
2 | Finance | Invoice to Pay | Invoice Processing | All category of invoices | QR validation with GST Portal | SAP-DCS | EXT-GST Portal |  | Real Time |  | SSL |  |  | #REF!
3 | Finance | Invoice to Pay | Invoice Processing | Job Work and Service confirmation | Custom mobile based application for creation & maintenance of service slips for job-work, repairs services etc. | EXT-MobileApp | SAP-VIM | Opentext | Real Time |  |  |  |  | #REF!
4 | Finance | Invoice to Pay | Invoice Processing | Job Work and Service confirmation in S4 | Custom mobile based application for creation & maintenance of service slips for job-work, repairs services etc. | EXT-MobileApp | SAP-S4 | Manmohan/Sunil | Real Time |  | Not Applicable | Not Applicable |  | #REF!
5 | Finance | Invoice to Pay | Payment Processing | Host to Host Payment - Hotels, HSBC Bank | Domestic Payments, Foreign Payments, Advance Payments, Ad-hoc / Urgent Payments IHCL to Bank Host to Host | SAP-S4 | EXT-BANK-HSBC |  | Real Time | H2H, HSBC | SFTP |  | Discussion Completed | #REF!
6 | Finance | Invoice to Pay | Payment Processing | Host to Host Payment - Hotels, HDFC Bank | Domestic Payments, Foreign Payments, Advance Payments, Ad-hoc / Urgent Payments IHCL to Bank Host to Host | SAP-S4 | EXT-BANK-HDFC |  | Real Time | H2H, HDFC | SFTP |  | Discussion Completed | #REF!
7 | Finance | Invoice to Pay | Payment Processing | Host to Host Payment - Corporate, Kotak Bank | Domestic Payments, Foreign Payments, Advance Payments, Ad-hoc / Urgent Payments IHCL to Bank Host to Host - | SAP-S4 | EXT-BANK-Kotak |  | Real Time | H2H, Kotak | SSL |  | Discussion Pending | #REF!
8 | Finance | Invoice to Pay | Payment Processing | Host to Host Payment - Corporate, Axis Bank | Domestic Payments, Foreign Payments, Advance Payments, Ad-hoc / Urgent Payments IHCL to Bank Host to Host - | SAP-S4 | EXT-BANK-Axis |  | Real Time | H2H, Axis | SSL |  | Discussion Pending | #REF!
9 | Finance | Invoice to Pay | Payment Processing | Host to Host Payment - Corporate, ICICI Bank | Domestic Payments, Foreign Payments, Advance Payments, Ad-hoc / Urgent Payments IHCL to Bank Host to Host - | SAP-S4 | EXT-BANK-ICICI |  | Real Time | H2H, ICICI | SSL |  | Discussion Pending | #REF!
10 | Finance | Invoice to Pay | Payment Processing | Statutory Payments - TDS/VAT/GST return | Payment executive to login on respective government site and generate draft challan for statutory payments | SAP-S4 | EXT-GOVT Pay |  |  |  | SSL |  |  | #REF!
11 | Finance | Expense Management | Payment Processing | Staff reimbursement | IHCL to Bank Host to Host - HDFC for Staff Reimbursement | SAP-S4 | EXT-BANK-HDFC |  |  | H2H, HDFC | SSL |  | Discussion Pending | #REF!
12 | Finance | Master Data | Master Data Management (customer) | Creation / Amendment / Change, Governance | Integration required from SAP MDG with CDM & from CDM to other upstream systems (POS, Spa, SNC Banquet bookings, Reservation system and PMS) Key Data - Name, Type (Registered, Unregistered, SEZ, Travel Agent), PAN, GSTN, IATA, City, Address | EXT-CDM | SAP S4 | Pranjal/Shilpa | Real Time | Yes | SSL |  | To be decided | #REF!
13 | Finance | Master Data | Master Data Management (customer) | Creation / Amendment / Change, Governance | To sync CDM master with SAP Customer master CDM Account Number, Name, Type (Registered, Unregistered, SEZ, Travel Agent), PAN, GSTN, IATA, City, Address | EXT-CDM | SAP-S4 | Pranjal/Shilpa | Real Time |  | Not Applicable | Not Applicable |  | #REF!
14 | Finance | Bill to Cash | Credit Limit Management | Permanent credit limit and temporary credit limit | SAP Credit Limit data to flow to Bolton for consolidation with Prologic data | EXT-Prologic | SAP-BI | Pranjal/Shilpa | Day-End Batch |  |  |  | To be decided | #REF!
15 | Finance | Bill to Cash | Credit Utilization Computation | Credit Utilization Computation | SAP Credit Limit data to flow to Bolton for consolidation with Prologic data Send Utilization to source system CDM Account Number, Name, Available Credit Limit, Credit Utilization | SAP-BI | EXT-PMS/POS | Pranjal/Shilpa | Day-End Batch |  |  |  |  | #REF!
16 | Finance | Bill to Cash | Billing | E-invoice data from Source to ERP - PMs Cloud | Billing Data on Checkout & Credit Note For e-invoice generation & settlement accounting Opera Cloud/POS Cloud to SAP-S/4 HANA | EXT-PMS.GST Cloud | SAP-S4 | Pranjal/Shilpa | Real Time |  | Not Applicable | Not Applicable |  | #REF!
17 | Finance | Bill to Cash | Billing | E-invoice data from Source to ERP - PMS On Prem | Billing Data on Checkout & Credit Note For e-invoice generation & settlement accounting Opera OnPrem instance pending for migration to cloud to SAP-S/4 HANA | EXT-PMS.GST Onprem | SAP-S4 | Pranjal/Shilpa | Day-End Flat file | E-invoice Generation | Not Applicable | Not Applicable |  | #REF!
18 | Finance | Bill to Cash | Billing | E-invoice data from Source to ERP - POS Cloud | Billing Data on settlement For e-invoice generation & settlement accounting POS Cloud to SAP-S/4 HANA for E-invoice generation through flat file post night audit for all POS outlets, Banquets and SPA | EXT-POS.GST | SAP-S4 | Pranjal/Shilpa | Day-End Flat file | E-invoice Generation | SFTP |  | Discussion Completed | #REF!
19 | Finance | Bill to Cash | Billing | Fetch EInvoice information from portal | SAP-S/4 HANA for E-invoice generation through SAP-DCS to GST portal through API | SAP-DCS | EXT-GST Portal | Diverse Infotech | Real Time | E-invoice Generation | SSL |  |  | #REF!
20 | Finance | Bill to Cash | Billing | Archiving Invoices and supporting documents | Collate E-invoice, Guest signed supporting invoices from PMS/POS into DMS system with feature to upload BTC letter and cover letters etc. vide Invoice number reference SAP S/4 HANA to DMS, repository of all signed supporting documents | SAP-S4 | EXT-DMS(Invoice) | David | Real Time | E-invoice Generation | SSL |  | Critical for digitisation of customer invoicing | #REF!
21 | Finance | Bill to Cash | Billing | Digital Signature of hotel FC on Invoices | Attach Digital Signature of unit head on documents | EXT-DMS(Invoice) | EXT-DSC(sign) | David | Real Time | E-invoice Generation | SSL |  | Critical for digitisation of customer invoicing | #REF!
22 | Finance | Bill to Cash | Billing | E-invoice generation | SAP S/4 Hana will send to Opera Cloud + POS for handing over the QR code generated Invoices | SAP-S4 | EXT-PMS.GST Cloud | David | Real Time | E-invoice Generation | SSL |  | Alternatively, Send the QR details to external DMS or Ecobillz till SAP solution is finalised | #REF!
23 | Finance | Bill to Cash | Billing | E-invoice generation | SAP S/4 Hana will send to Opera Cloud + POS for handing over the QR code generated Invoices | SAP-S4 | EXT-POS.GST | David | Real Time | E-invoice Generation | SSL |  | Alternatively, Send the QR details to external DMS or Ecobillz till SAP solution is finalised | #REF!
24 | Finance | Bill to Cash | Billing | Dispatch of Invoice to Customers | Auto dispatch E-invoice, Guest signed supporting invoices from PMS/POS, BTC letter to be sent via email to booker/ Company bill to addresses | EXT-DMS(Invoice) | Outlook email services | David | Real Time |  | SSL |  | External integration to get guest signed digital invoice and supporting from Source system to DMC is not considered in Finance scope | #REF!
25 | Finance | Bill to Cash | Revenue Accounting | Revenue Accounting – PMS | After night audit line level unbilled revenue, revenue data(along with market segment) will be sent from Opera to SAP S/4 HANA Opera (Cloud & Onprem) to SAP-S/4 HANA for Revenue accounting and for Customer Advance / Deposit Receipts | EXT-PMS(RV/ST) | SAP-S4 | Pranjal/Shilpa | Day-End Flat file | Revenue & Settlement Accounting | Not Applicable | Not Applicable |  | #REF!
26 | Finance | Bill to Cash | Revenue Accounting | Revenue Accounting – POS | After night audit line level unbilled revenue, revenue data(along with market segment) will be sent from POS outlet, Banquets, SAP to SAP S/4 HANA POS (Cloud) to SAP-S/4 HANA for Revenue accounting | EXT-POS(RV/ST) | SAP-S4 | Pranjal/Shilpa | Day-End Flat file | Revenue & Settlement Accounting | SFTP |  | Discussion Completed | #REF!
27 | Finance | Bill to Cash | Revenue Accounting | Guest Ledger / Unbilled Revenue | After night audit line level unbilled revenue, revenue data(along with market segment) will be sent from Opera to SAP. Opera (Cloud & Onprem) to SAP-S/4 HANA for Unbilled Revenue accounting | EXT-PMS.OSO | SAP-S4 | Pranjal/Shilpa | Day-End Flat file | MSO file | Not Applicable | Not Applicable |  | #REF!
28 | Finance | Bill to Cash | Cash Application | All category of collections and cash applications | Receiving MT940 from Bank and sharing payment files to Bank | EXT-Banks(Rec) | SAP-S4 | Ankita |  |  | Not Applicable | Not Applicable | Discuss with Ankita | #REF!
29 | Finance | Bill to Cash | Cash Application | Travel Agents | Receiving MT940 from Bank and sharing payment files to Bank Downloading reports from TA website and file formatting - RPA to upload verified reports in SAP | EXT-TA website | SAP-S4 | Ankita |  |  | Not Applicable | Not Applicable |  | #REF!
30 | Finance | Bill to Cash | Cash Application | Epicure membership - point earned/ burned | Update points data from Epicure source system to SAP S/4 HANA | EXT-Epicure | SAP-S4 | David |  | Epicure | Not Applicable | Not Applicable |  | #REF!
31 | Finance | Bill to Cash | Cash Application | Gift Card - issued/ encashed | Update points data from Epicure source system to SAP S/4 HANA | EXT-Gift card | SAP-S4 | David |  |  | Not Applicable | Not Applicable |  | #REF!
32 | Finance | Record to Report | Period end close | Recurring Journals posting – TDS entry posting in GL | JV request management - third party BPM tool Configure Workflow tool to include mandatory TDS check at the time of requesting JVs and mandatory check for set of GLs Cost Centres where gifts, perquisites are typically recorded | EXT-BPM(R2R) | SAP-S4 | Ankita |  |  | Not Applicable | Not Applicable | SAP-BPM, not available | #REF!
33 | Finance | Record to Report | Period end close | Inventory, Liquor Consumption – POS | After night audit line level Item level POS data (along with market segment) will be sent from POS outlet, Banquets, SAP to SAP S/4 HANA POS (Cloud) to SAP-S/4 HANA for Liquor Inventory consumption | EXT-POS(DT) | SAP-S4 | Pranjal/Shilpa | Day-End Flat file | Inventory, Liquor consumption | SFTP |  | Discussion Completed | #REF!
34 | Finance | Record to Report | Intercompany | Intercompany accounting between SAP entities for trade & non-trade transactions | DMS to save invoices references for intercompany transactions between AP & AR modules | EXT-DMS(IC) | SAP-S4 | Mohan |  | DMS for Intercompany | Not Applicable | Not Applicable | Explore SAP-VIM as DMS for IC invoices | #REF!
35 | Finance | Fixed Assets | Creation & Sale/Disposal of Asset | Creation of Asset, WBS code, CWIP code and Request for Sale/Disposal | BPM tool as a workflow solution for CAPEX creation & budget approval (non projects) requests BPM tool as a workflow solution for asset sale & disposal approval requests | EXT-BPM(FA) | SAP-S4 | Shamal |  |  | Not Applicable | Not Applicable | To be discussed | #REF!
36 | Finance | Fixed Assets | Tagging of Assets | Tagging & physical verification | RFID tagging solution for selected category of assets (high risk / high value) | EXT-RFID(FA) | SAP-S4 | Shamal |  |  | Not Applicable | Not Applicable |  | #REF!
37 | Finance | Planning, Budgeting & Forecasting | MIS reporting from PBCS | Integrating trial balance data from units to PBCS | Trial balance from SAP-S4/Hana, Non SAP units into PBCS | SAP-S4 | EXT-PBCS | Ankita |  | FP&A | SSL |  |  | #REF!
38 | Finance | Hyperion Financial Management (HFM) | Financial Consolidation | Integrating trial balance data from units to HFM | Trial balance from SAP-S4/Hana, Non SAP units into HFM | SAP-S4 | EXT-HFM | Ankita |  | HFM | SSL |  |  | #REF!
39 | Finance | Tax Audit | Tax Audit | Tax Audit data | Consolidation of Tax Audit clauses, Separate application built by NWDCo | SAP-S4 | EXT-Tax Audit | Sunil |  | Tax Audit consolidation (NWDCo) | SSL |  |  | #REF!
40 | Finance | Control Centre | Asset, Liability & Cost analysis | Control Centre Analysis data | Data sent by Oracle to Datalake | SAP-S4 | EXT-Control | Shamal |  | Protiviti control centre | SSL |  |  | #REF!
41 | Finance | Reporting and compliance of RPT | RPT Transactions | RPT Transactions Data | Application built on Anaplan by Deloitte Transaction Data to be sent by SAP to Deloitte-Anaplan application | SAP-S4 | EXT-Anaplan | Ankita |  | Related Party Transactions (RPT) (Deloitte-Anaplan) | SSL |  |  | #REF!
42 | Procurement | Source to Contract | Contract Management | Contract Creation | SAP ARIBA | SAP-Ariba | EXT-DMS | Prabhakaran | [5 empty] | #REF!
43 | Procurement | Source to Contract | Vendor Management | Query / compliant management | SAP BTP / Third-Party Bolt On solution System should be able to category request as query, compliant, etc., and should be able to track creation, assignment, resolution, closure along with monitoring reports | SAP-BTP | EXT-TicketingTool | ??? | [5 empty] | #REF!
44 | Procurement | Source to Contract | Category Management | Category Analysis | SAP Ariba Category Management Integration with third-party sources for market analysis | SAP-Ariba | EXT-Market Analysis | Prabhakaran | [5 empty] | #REF!
45 | Procurement | Master Data | Vendor Master | Vendor Onboarding | Third Party APIs for document related validations | SAP-Ariba | EXT-GST Portal | Nileshwar | [5 empty] | #REF!
46 | Procurement | Master Data | Vendor Master | Vendor Onboarding | Third Party APIs for document related validations | SAP-Ariba | EXT-MSME Portal | Nileshwar | [5 empty] | #REF!
47 | Procurement | Master Data | Vendor Master | Vendor Onboarding | Third Party APIs for document related validations | SAP-Ariba | EXT-GST Portal | Nileshwar | Real Time |  |  |  |  | TCS-EXT
48 | Procurement | Master Data | Vendor Master | Vendor Onboarding | Third Party APIs for document related validations | SAP-Ariba | EXT-MSME Portal | Nileshwar | Real Time |  |  |  |  | TCS-EXT
49 | Procurement | Master Data | Vendor Master | Vendor Onboarding | Third Party APIs for document related validations | SAP-Ariba | EXT-FSSAI Portal | Nileshwar | Real Time |  |  |  |  | TCS-EXT
50 | Procurement | Master Data | Vendor Master | Vendor Onboarding | Third Party APIs for document related validations | SAP-Ariba | EXT-PAN Portal | Nileshwar | Real Time |  |  |  |  | TCS-EXT
51 | Procurement | Master Data | Vendor Master | Vendor Onboarding | Third Party APIs for document related validations | SAP-Ariba | EXT-CIN Portal | Nileshwar | Real Time |  |  |  |  | TCS-EXT
52 | Procurement | Master Data | Vendor Master | Vendor Onboarding | Third Party APIs for Bank Account verification / Penny Drop related validations | SAP-Ariba | EXT-Bank Account Portal | Nileshwar | Real Time |  |  |  |  | TCS-EXT
53 | Procurement | Source to Contract | Contract Management | Contract Integration ¦ GBPA to CPA replication | Auto replication of contract terms & parameters (Price, payment terms, products etc) through RPA | SAP-Ariba | EXT-RPA | Nileshwar | Real Time |  |  |  |  | TCS-EXT
54 | Procurement | Source to Payment | Invoicing | SES / Invoice Processing | SES & Vendor Invoice transmission to VIM through Ariba | SAP-Ariba | EXT-VIM | Nileshwar | Real Time |  |  |  |  | TCS-EXT